## Slide 1
Plan Procurement Management
Inputs
Notes: 1

## Slide 2
Plan Procurement Management
Plan Procurement Management
What could be an input?
Tools & Techniques
?
Outputs
Notes: 2
2

## Slide 3
Inputs
  How much does it cost to make a promotional video for a marketing campaign?
  $5,000
  Hours worked times hourly rate, plus 20%
  $2,000 to start, $2,000 when finished, plus $1000 if finished in less than 7 days
  $1000 plus 10% of produced revenue for the next 3 months
  Hourly rate of a camera operator and a video editor, plus the cost of any goods or services they need to do the work
  How can we plan to approach video production companies?
Plan Procurement Management
Notes: 3
3

## Slide 4
 | Project Integration Management | Project Scope Management | Project Schedule Management | Project Cost Management | Project Quality Management | Project Resource Management | Project Communications Management | Project Risk Management | Project Procurement Management | Project Stakeholder Management
Initiating Process Group | -Develop Project Charter |  |  |  |  |  |  |  |  | -Identify Stakeholders
Planning Process Group | -Develop Project Management Plan | -Plan Scope Management -Collect Requirements -Define Scope -Create WBS | -Plan Schedule Management -Define Activities -Sequence Activities -Estimate Activity Durations -Develop Schedule | -Plan Cost Management -Estimate Costs -Determine Budget | -Plan Quality Management | -Plan Resource Management -Estimate Activity Resources | -Plan Communications Management | -Plan Risk Management -Identify Risks -Perform Qualitative Risk Analysis -Perform Quantitative Risk Analysis -Plan Risk Responses | -Plan Procurement Management | -Plan Stakeholder Engagement
Executing Process Group | -Direct and Manage Project Work -Manage Project Knowledge |  |  |  | -Manage Quality | -Acquire Resources -Develop Team -Manage Team | -Manage Communications | -Implement Risk Responses | -Conduct Procurement | -Manage Stakeholder Engagement
Monitoring and Controlling Process Group | -Monitor and Control Project Work -Perform Integrated Change Control | -Validate Scope -Control Scope | -Control Schedule | -Control Cost | -Control Quality | -Control Resources | -Monitor Communications | -Monitor Risks | -Control Procurement | -Monitor Stakeholder Engagement
Closing Process Group | -Close Project or Phase |  |  |  |  |  |  |  |  | 
Project Management Process Group and Knowledge Area Mapping
PMBOK® Guide, 6th Edition, Table 1-4, p. 25
Project Procurement Management
Notes: 4
4

## Slide 5
Plan Procurement Management
Plan Procurement Management
  Is the process of documenting the project procurement decisions, as well as determining the approach that will be taken to identify potential sellers.
Key Benefit
  It determines whether to acquire the needed goods or services from outside the project as well as how to go about acquiring these resources
Notes: 5
5

## Slide 6
Process
Inputs
?
?
… ?
Tools & Techniques
Outputs
Procurement management plan
Procurement strategy
Bid documents
Procurement statement of work
Source selection criteria
Make-or-buy decisions
Independent cost estimates
Change requests
Project documents updates
Organizational process assets updates
PMBOK® Guide, 6th Edition, Figure 12-2, p. 466
Plan Procurement Management
Plan Procurement Management
Notes: 6
6

## Slide 7
Process
Inputs
Project charter
Business documents
Project management plan
Project documents
Enterprise environmental factors
Organizational process assets
Tools & Techniques
Outputs
PMBOK® Guide, 6th Edition, Figure 12-2, p. 466
Plan Procurement Management
Plan Procurement Management
Notes: 7
7

## Slide 8
Inputs
  Inputs:
  Project charter
    Objectives
    project description
    summary milestones
    preapproved financial resources
Plan Procurement Management
Notes: 8
8

## Slide 9
Inputs
  Inputs:
  Business documents
    Business Case Procurements must fulfill the business case to be of value
    Benefits management plan When are specific benefits from the business case expected?
Plan Procurement Management
Notes: 9
9

## Slide 10
Inputs
  Inputs:
  Project management plan
    Scope management plan Manage the scope of work (and procurement)
    Quality management plan Applicable industry standards and codes that must be followed.
    Resource management plan Constraints that influence resource procurement, including Buy / Lease / Rent
    Scope baseline Scope statement, WBS, WBS dictionary. Scope definition drives statement of work (SOW) and terms of reference (TOR)
Plan Procurement Management
Notes: 10
10

## Slide 11
Inputs
  Inputs:
  Project documents
    Milestone list
    Project team assignments
    Requirements documentation
    Requirements traceability matrix
    Resource requirements
    Risk register
    Stakeholder register
Plan Procurement Management
Notes: 11
11

## Slide 12
Inputs
Plan Procurement Management
  Inputs:
  Enterprise environmental factors
    Factors that can influence the procurement management process can include
    market conditions, supply and demand variations
    products and services available in the market place
    international laws (requires expert knowledge)
    local laws (even when commonly understood)
    availability of qualified labour
    unions
    availability of and conditional requirements for specialized manufacturing
    ethical considerations
    Systems for contract management, accounting, and payments
    Pre-qualified sellers
    Any factor in the project’s environment that influences procurement
Notes: 12
12

## Slide 13
Inputs
Plan Procurement Management
  Inputs:
  Organizational process assets
    Existing contracts and policies within your organization that impact the plan procurement management process:
    preapproved sellers list
    formal procurement policies
    procedures
    guidelines
    Various contract types
Notes: 13
13

## Slide 14
Inputs
Plan Procurement Management
  Contract Types:
  Fixed Price
    Firm fixed price (FFP)
    Fixed price incentive fee (FPIF)
    Fixed price with economic price adjustments (FPEPA)
  Cost Reimbursable
    Cost plus fixed fee (CPFF)
    Cost plus incentive fee (CPIF)
    Cost plus award fee (CPAF)
  Time and Material (T&M)
Notes: 14
14

## Slide 15
Inputs
Plan Procurement Management
Contracts
  A contract is a mutually binding agreement between a buyer and a seller that obligates the seller to provide the specified product, service or result and obligates the buyer to make the payment for it
Notes: 15
15

## Slide 16
Inputs
Plan Procurement Management
Essential Elements of a Contract
  An Offer
  Mutual Agreement/Acceptance
    Written words
    Conduct
    Spoken words
  Consideration – The Inducement to a Contract
    The cause, motive, price, influence that induces a contracting party to enter into a contract
  Legality of Purpose
  Competent Parties/Contract Capability
    Binding only if contractor has capability, ability, or authority to make binding commitments
Notes: 16
16

## Slide 17
Inputs
Plan Procurement Management
  Contracts can be oral or written—although written is preferred
  Canada backs all contracts through the court system
  Contracts should clearly state all requirements for product acceptance
  Any changes to the contract must be formally approved, controlled and documented
  A contract is NOT fulfilled until ALL of its requirements are met
Notes: 17
17

## Slide 18
Inputs
Plan Procurement Management
Why Contract?
  Rule of Law (legally binding)
  Develops & maintains a professional business relationship between the buyer & the seller
  Written documents that confirm and communicate the agreement between buyer & seller
    Promote understanding between parties
    Put in place to avoid litigation in the event of a dispute
    Used to protect parties in the event of a litigation
Economics | Specialization Required | Shift Business Risk
Fewer worker benefits | Specialized products and services | Can change vendors
Less inventory and storage |  | Leaner operations
Maintain flexibility |  | 
Increase profitability |  | 
Notes: 18
18

## Slide 19
Inputs
Plan Procurement Management
Notes: 19
19

## Slide 20
Inputs
Plan Procurement Management
Non-Competitive Contracting Methods
  Purchase Agreements
    Used when 2 parties expect to deal with one another repeatedly over a long period of time
    Agree to the terms and conditions that will apply to any transaction between them
    Agreement not a contract until the buyer issues an order; if accepted by seller will become a contract
  Sole Source
    Only one seller that can provide the needed product (monopoly in its market)
  Single Source
    Preference for a specific seller
Notes: 20
20

## Slide 21
Inputs
Plan Procurement Management
  Simplified Competitive Contracting Methods
  Purchase Cards
    A company charge card that allows goods and services to be procured without utilising a traditional purchasing process
    Issued to employees trained in their organization’s policies and procedures related to P-Card use
Notes: 21
21

## Slide 22
Inputs
Plan Procurement Management
Petty Cash
  Small amount of discretionary funds in the form of cash given to a custodian
  Expenditures are made against vouchers
  At any given time the total of cash on hand plus reimbursed vouchers must equal the original fund
  When the fund gets low, the custodian submits the vouchers for reimbursement and the fund is topped up
Notes: 22
22

## Slide 23
Inputs
Plan Procurement Management
Auctioning
  The development of the internet has led to a significant rise in the use of auctions
  In 2008, the National Auctioneers Association reported that the gross revenue of the auction industry for that year was approximately $268.4 billion, with the fastest growing sectors being agricultural, machinery, and equipment auctions and residential real estate auctions
Notes: 23
23

## Slide 24
Inputs
Plan Procurement Management
Competitive Contracting Methods
  Sealed Bidding
    Buyer makes solicitation for firm bids
    After deadline, bid opening
    Buyer chooses seller based typically on low price
Notes: 24
24

## Slide 25
Inputs
Plan Procurement Management
Two-Stepped Sealed Bidding
  Seller submits technical proposal, management and company qualification information
  Buyer evaluates everything except pricing information to determine which sellers are qualified
  Buyer requests pricing information from qualified sellers
  Buyer chooses seller (usually lowest bidder)
Notes: 25
25

## Slide 26
Inputs
Plan Procurement Management
Competitive Proposals or Negotiations
  Request For Proposal (RFP) or Seller Proposal
  Proposal analysis – technical and/or cost
  Short list
  Negotiations
  Final evaluation and selection
  Award of contract
  Performance
Notes: 26
26

## Slide 27
Inputs
Plan Procurement Management
Contract Types
  Fixed-price or lump-sum contracts
    The buyer pays the seller the set amount as defined by the contract regardless of the seller’s costs
    Seller is motivated to decrease costs by producing efficiently
  Cost-reimbursable contracts
    Buyer reimburses seller for seller’s allowable costs plus a fee calculated factor from the costs
    Seller is motivated to maintain his fee
  Time and Materials (T&M) contracts
Notes: 27
27

## Slide 28
Inputs
Plan Procurement Management
Contract Types
  Indefinite delivery indefinite quantity contracts (IDIQ)
    State type of service to be delivered and length of time (usually 5 year) during which the services can be requested, and the minimum and maximum contract amount
  Multiple award schedules
    Used when there is a generally accepted “reasonable price” for a good or service
    Each potential seller submits its qualifications and schedule of rates
    Seller is selected on the offer which is most advantageous to the government
    Once approved government agencies can buy goods and services at the published rate without a separate competition
    Often adopted as a strategic sourcing initiative
Notes: 28
28

## Slide 29
Inputs
Plan Procurement Management
FFP: Firm Fixed Price Contract
  The work is completed for a predetermined price. Benefits the buyer. Seller at risk if item isn’t clearly defined. Seller must manage changes closely.
FPIF: Fixed Price Incentive Fee Contracts
  Similar to fixed price, but an incentive is offered for a predetermined goal (eg: early completion). More administrative effort for buyer and seller.
FP-EPA: Fixed Price with Economic Price Adjustment Contract
Purchase Order
  A form of fixed price, usually for off-the-shelf items. Optimal for both parties when item is a commodity (such as computers, stationary, pipe, valves, instruments)
Notes: 29
29

## Slide 30
Inputs
Plan Procurement Management
Firm Fixed Price (FFP) Example:
Seller Estimated Costs = $1,000K
Seller Profit (@ 10%) = $100K
Contract Value = $1,100K
A | Final Cost Seller Bills Buyer Pays | $800K $1100k $1100K | Seller makes an additional $200K profit | Buyer oblivious of costs or extra profit being made
B | Final Cost Seller Bills Buyer Pays | $1,300K $1100k $1100K | Seller makes no profit and incurs a loss of $200K | Buyer oblivious of losses being incurred
Notes: 30
30

## Slide 31
Inputs
Plan Procurement Management
Notes: 31
31

## Slide 32
Inputs
Plan Procurement Management
Subjective Incentives
  Award Fee
    Can have either the entire fee structure, or portion of the fee, subject to the buyer’s subjective judgment of the contractor’s performance against predetermined criteria contained in an award fee plan
    Does NOT include predetermined targets and automatic profit or fee adjustment formulas
    The award fee determination is judgmental based on periodic evaluations of ongoing contractor performance made unilaterally by the buyer
    Negotiate estimated cost, as well as amount of money, to be included in an award fee pool
    Becomes part of the contract
Notes: 32
32

## Slide 33
Inputs
Plan Procurement Management
Fixed Price Plus Incentive Fee (FPIF) Example:
  Target Cost = $1,000K
  Target Price = $1,100K
  Share Ratio = 70/30
  Target Profit = $100K
  Ceiling Price = $1,200K
A | Final Cost Seller Bills Buyer Pays | $800K $800K+$100K+$60K=$960K $960K | Seller makes an additional $60K profit | Buyer aware of costs and the profits being made
B | Final Cost Seller Bills Buyer Pays | $1,300K $1,200K $1,200K | Seller makes no profit and incurs a loss of $100K | Buyer aware of costs and of losses being incurred
Notes: 33
33

## Slide 34
Inputs
Plan Procurement Management
Point of Total Assumptions (PTA)
  Only applies to FPIF contracts
  The point at which the share ratio ceases to operate and $1 of added cost results in $1 of decreased payment to the seller
  Formula
  PTA = Ceiling Price – Target Price + Target Cost
  Buyer Share
Notes: 34
34

## Slide 35
Inputs
Plan Procurement Management
Notes: 35
35

## Slide 36
Inputs
Plan Procurement Management
Point of Total Assumptions (PTA) Example:
  Target Cost = $100 M
  Target Profit = $15 M
  Target Price = $115 M
  Ceiling Price = $130 M
  Share Ratios (Seller ‘share’ variance of cost, affects Seller profit in the following ratios):
    Overrun 85% /15%
    Underrun 50% /50%
PTA = $130M - $115M + $100M = $117.6M
.85
Notes: 36
36

## Slide 37
Inputs
Plan Procurement Management
Cost-Plus-Fee (CPF)
  Buyer reimburses seller for seller’s allowable costs
  Seller also receives a fee calculated as an agreed upon percentage of costs
    Fee varies with actual cost
Cost-Plus-Fixed-Fee (CPFF)
  Buyer reimburses seller for seller’s allowable costs (defined by contract) plus a fixed amount of profit (fee)
Cost-Plus-Incentive-Fee (CPIF)
  Buyer reimburses seller for seller’s allowable costs (defined by contract)
  Seller earns profit if it meets defined performance criteria
Notes: 37
37

## Slide 38
Inputs
Plan Procurement Management
Cost-Reimbursable Contracts
  Two components – Actual Costs + Profit
Actual Costs fall into two categories:
  Direct Costs are costs incurred directly associated with specific project tasks such as:
    Labour
    Materials
  Indirect Costs are costs distributed/allocated across the project such as:
    Utilities
    Office space
    Overhead costs
    Computer systems
Notes: 38
38

## Slide 39
Inputs
Plan Procurement Management
Cost-Plus-Fixed-Fee (CPFF) Example:
  Estimated Cost = $1,000K
  Fixed Fee at 10% = $100K
  Estimated Total Cost = $1,100K
A | Final Cost Seller Bills Buyer Pays | $900K $900K+$100K=$1000K $1,000K | Seller still makes his $100K profit but his margin is now 11.1% | Buyer aware of costs and the profit being made
B | Final Cost Seller Bills Buyer Pays | $1250K $1250K+$100K=$1350K $1,350K | Seller still makes his $100K profit but his margin is now 8.0% | Buyer aware of costs and of profit
Notes: 39
39

## Slide 40
Inputs
Plan Procurement Management
Time and Material (T&M) Contracts
  Open-ended hybrid of cost-reimbursable and fixed-price arrangements where elements of both are used
  Full value of agreement and quantity of items to be delivered are not defined by the buyer at the time of the contract award
  A fixed unit rate can be set for certain elements of work while other components are completely reimbursable
Good Practice to have a “Not-To-Exceed” Quantities or “Time Limit” clauses
Notes: 40
40

## Slide 41
Inputs
Plan Procurement Management
Time and Materials Example:
  Installation of a concrete pile $30,000
  Initial estimated quantity 100
  Not to exceed quantity 120
A | Final # Piles Seller Bills Buyer Pays | 95 95 @ $30K each =$2,850K $2,850K | Seller’s profit margin is in the $30K
B | Final # Piles Seller Bills Buyer Pays | 110 110 @ $30K each =$3,300K $3,300K | Seller’s max exposure 120 @ $30K each = $3,600K
Notes: 41
41

## Slide 42
Inputs
Plan Procurement Management
Contract | Buyer’s Risk | Seller’s Risk
Cost Plus Percentage Cost | Highest Risk | Low Risk
Cost Plus Fixed Fee | High Risk | Low Risk
Cost Plus Incentive Fee | Medium Risk | Low Risk
Fixed Price | Low | High
Time & Material | Low if it includes NTE High if excludes NTE | High – If it is original unit rate, estimate is flawed Low – If it is original unit rate, estimate is sound
Risk Comparison of Types of Contracts
Notes: 42
42

## Slide 43
Inputs
Plan Procurement Management
Project Delivery Method
How much input/control the owner needs or desires
  Design–Bid–Build
    Traditional – the design and execution are performed by separate entities with a bid cycle between the design and the execution
  Design–Build
    Design and execution are performed by one entity
  Turn Key
    One entity responsible from concept to initial start-up & commissioning
  Design–Build–Operate–Maintain-Transfer (DBOM)
    One entity responsible from concept to a stable, performing operation
Notes: 43
43