## Slide 1
Plan Procurement Management
Notes: 1

## Slide 2
Objectives
Project Procurement Management
What is procurement?
Notes: 2
2

## Slide 3
Objectives
Project Procurement Management
Procurement is:
External goods and services
  Labour (Human Resources)
  Tools
  Raw Materials
  Finished Products
  Services
  Utilities
  Anything from a 3rd party source (outside the client and outside your organization)
Notes: 3
3

## Slide 4
Objectives
Project Procurement Management
Internal resources, goods, and services are:
Not procured
Managed by all the other PMP processes
Notes: 4
4

## Slide 5
Objectives
Project Procurement Management
Procurement is:
Sourcing and finding
  How do you determine where good and services that meet your project’s requirements can be sourced from?
Notes: 5
5

## Slide 6
Objectives
Project Procurement Management
Procurement is:
Negotiating and agreeing to terms and conditions
  Even buying commodity supplies requires agreement to the pre-existing terms of the supplier.
  Specialized goods and services often requires negotiated terms or custom quoted terms.
Notes: 6
6

## Slide 7
Objectives
Project Procurement Management
Commodity supplies:
COTS – Commercial Off The Shelf
Buy from a retail store
Buy from a wholesaler or distributer
Terms:
Pre-existing terms, usually industry standard store policies or manufacturer terms.
Warranty, return, etc.
Notes: 7
7

## Slide 8
Objectives
Project Procurement Management
Specialized goods and services:
Custom quotes
Often requires negotiated terms or
custom quoted terms.
Notes: 8
8

## Slide 9
Objectives
Project Procurement Management
Procurement is:
Methods of price optimization
  Could it cost less, or be done faster, or better, using outside resources?
  What is our organization’s history or current best practice with procurement policy?
  What are industry trends or emerging methods for managing procurement?
  Does the project need to worry about competition for the supply of certain resources? Should we secure a supply and price as early as possible, or can we wait?
Notes: 9
9

## Slide 10
Objectives
Project Procurement Management
Procurement is:
Ensuring delivery
  Our suppliers have suppliers … how is that supply chain being managed?
  When we commit to placing an order, what can we do to help guarantee the goods and services will be delivered to the right place at the right time, along with any special instructions or considerations required to complete a given activity or work package?
Notes: 10
10

## Slide 11
Objectives
Project Procurement Management
Procurement requires dedicated management processes because:
External sources require external terms
The project charter, project scope, and any terms between your organization and your client do not cover terms set by third party suppliers (external sources)
Procurement adds External RISK
Notes: 11
11

## Slide 12
Objectives
Project Procurement Management
Supplier Relations (for each supplier):
Existing relationship between your organization and the supplier?
Do any project stakeholders (within the client, your organization, or otherwise) have any interest or relationship with the supplier outside the scope of the project?
Is the supplier a stakeholder in this project?
Notes: 12
12

## Slide 13
Objectives
Project Procurement Management
Why do we need procurement?
Notes: 13
13

## Slide 14
Objectives
Project Procurement Management
We need Procurement because:
Even in normal run-rate business, goods and services generally need to be acquired from outside the organization.
Projects are by definition not business as usual, meaning they tend to require more goods and services procured from outside the organization than run-rate business does.
Notes: 14
14

## Slide 15
Objectives
Project Procurement Management
Does your personal example project
need procurement?
Notes: 15
15

## Slide 16
Objectives
Project Procurement Management
Do these projects needs procurement?
Organize a day of kite flying in a field
Ship a backup generator to a remote site
Test and deploy an emergency software patch to servers in data centres on different continents
Construct a building
Move company office space to a different floor in the same building
Add a small kitchen with hot drink (coffee, tea) capacity to an office space
Notes: 16
16

## Slide 17
Objectives
Project Procurement Management
Mars Habitat Project
Does your team’s organization need procurement to:
  Produce the design for habitat?
  Actually build the habitat?
Who procured your team’s organization?
  In that sense the project you are managing for your assignments is itself being managed by Procurement Management processes run by another organization. Your project is a supplier for that purpose.
Notes: 17
17

## Slide 18
Objectives
Project Procurement Management
Even when projects do not explicitly require procurement, it is important to understand
why procurement management may or may not be valuable to your project
how procurement management works
Considering procurement concepts will offer you additional perspective when addressing other open questions in your project management planning.
Notes: 18
18

## Slide 19
Project Procurement Management
The process of purchasing and acquiring products, services, or results needed that exists outside the project team.
Project Procurement Management
Introduction
Key Benefit
  It determines whether to acquire outside support and if so what to acquire, how to acquire it, how much is needed and when to acquire it
Notes: 19
19

## Slide 20
Project Procurement Management
Introduction
Scope
Time
Cost/Resources
Procurement is one of
the key levers you have
to help manage the
project’s triple constraints
Notes: 20
20

## Slide 21
Project Procurement Management
Introduction
Notes: 21
21

## Slide 22
Objectives
Project Procurement Management
What is there to manage?
Do you plan according to each supplier’s schedule? OR
Do suppliers plan according to your schedule?
Notes: 22
22

## Slide 23
Objectives
Project Procurement Management
How does it impact other knowledge areas?
Integration
Scope
Schedule
Cost
Quality
Resource
Communications
Risk
Stakeholder
Notes: 23
23

## Slide 24
Project Procurement Management
Institute for Supply Management™ (ISM)
  The identification, acquisition, access, positioning, management of resources and related capabilities the organization needs or potentially needs in the attainment of its strategic objectives
Procurement = External Supply
Source: Jan 2013 ISM WEB Site http//www.ism.ws
Introduction
Notes: 24
24

## Slide 25
Project Procurement Management
Introduction
Notes: 25
25

## Slide 26
Inputs
  PMBOK Sixth Edition – Procurement Management Processes:
  12.1 Plan Procurement Management
    The process of documenting project procurement decisions, specifying the approach, and identifying potential sellers.
  12.2 Conduct Procurements
    The process of obtaining seller responses, selecting a seller, and awarding a contract.
  12.3 Control Procurements
    The process of managing procurement relationships, monitoring contract performance, and making changes and corrections as appropriate.
  … Close Procurement Phase
    When all procurement is complete, review, complete, and close out all project documents pertaining to procurement.
Plan Procurement Management
Notes: 26
26

## Slide 27
 | Project Integration Management | Project Scope Management | Project Schedule Management | Project Cost Management | Project Quality Management | Project Resource Management | Project Communications Management | Project Risk Management | Project Procurement Management | Project Stakeholder Management
Initiating Process Group | -Develop Project Charter |  |  |  |  |  |  |  |  | -Identify Stakeholders
Planning Process Group | -Develop Project Management Plan | -Plan Scope Management -Collect Requirements -Define Scope -Create WBS | -Plan Schedule Management -Define Activities -Sequence Activities -Estimate Activity Durations -Develop Schedule | -Plan Cost Management -Estimate Costs -Determine Budget | -Plan Quality Management | -Plan Resource Management -Estimate Activity Resources | -Plan Communications Management | -Plan Risk Management -Identify Risks -Perform Qualitative Risk Analysis -Perform Quantitative Risk Analysis -Plan Risk Responses | -Plan Procurement Management | -Plan Stakeholder Engagement
Executing Process Group | -Direct and Manage Project Work -Manage Project Knowledge |  |  |  | -Manage Quality | -Acquire Resources -Develop Team -Manage Team | -Manage Communications | -Implement Risk Responses | -Conduct Procurement | -Manage Stakeholder Engagement
Monitoring and Controlling Process Group | -Monitor and Control Project Work -Perform Integrated Change Control | -Validate Scope -Control Scope | -Control Schedule | -Control Cost | -Control Quality | -Control Resources | -Monitor Communications | -Monitor Risks | -Control Procurement | -Monitor Stakeholder Engagement
Closing Process Group | -Close Project or Phase |  |  |  |  |  |  |  |  | 
Project Management Process Group and Knowledge Area Mapping
PMBOK® Guide, 6th Edition, Table 1-4, p. 25
Project Procurement Management
Notes: 27
27

## Slide 28
Plan Procurement Management
Plan Procurement Management
  Is the process of documenting the project procurement decisions, as well as determining the approach that will be taken to identify potential sellers.
Key Benefit
  It determines whether to acquire the needed goods or services from outside the project as well as how to go about acquiring these resources
Notes: 28
28

## Slide 29
Process
Inputs
Project charter
Business documents
Project management plan
Project documents
Enterprise environmental factors
Organizational process assets
Tools & Techniques
Expert judgment
Data gathering
Data analysis
Source selection analysis
Meetings
Outputs
Procurement management plan
Procurement strategy
Bid documents
Procurement statement of work
Source selection criteria
Make-or-buy decisions
Independent cost estimates
Change requests
Project documents updates
Organizational process assets updates
PMBOK® Guide, 6th Edition, Figure 12-2, p. 466
Plan Procurement Management
Plan Procurement Management
Notes: 29
29